## Sheet1
Iteration 1
Date | Software Application | Document
2016-07-24 | set up Google Drive,
2016-07-25 | set up VM, set up git hub, set up IDE | Start Document, set structure
2016-07-26 | Ms Project baseline, security library, Exceptions framework, build database
2016-07-27 | Quality dashboard, build server, Junit
2016-07-28 | Neural Network Start Implementation Model 3 | Sequence diagram
2016-07-29 | Continue Neural network model 3
2016-07-30 | Build Database | ER Diagram
2016-07-31 | Train Model 3 | Class Diagram
2016-08-01 | Train Model 3 | AI Module discussion
2016-08-02
2016-08-03 | Build UI - Enter information
2016-08-04 | Build UI - Enter information
2016-08-05 | Build UI - View | UI Diagram
2016-08-06